## Sheet1
Gantt chart (Project 2)
Activity | Week 1 (23/01/17) | Week 2 (30/01/17) | Week 3 (6/02/17) | Week 4 (13/02/17) | Week 5 (20/02/17) | Week 6 (27/02/17) | Week 7 (6/03/17) | Week 8 (13/03/17) | Week 9 (20/03/17) | Week 10 (27/03/17) | Week 11 (03/04/17)
Usability test on a website
Requirements & Expectations:
Create a project plan
Gantt Chart
Create sitemap
Site map /prototype
Create a ‘site-map’ for the system
Produce a paper prototype
Plan tests of the prototype
Test paper prototype
Test Paper prototype and analyse findings and present. Identify changes required
Run usability tests on the paper prototype
Analyse results and identify required changes
Begin coding
Start coding up your system
Continue coding
Usability test on a website
Analyse results and identify required changes
Requirements anlysis
Start work on beta product
Continue work on beta product
Group report
Vivas
Key:
Actual time it took us
Estimated time